## Roadmap
WeekStart | WeekEnd | Tasks | Owner | Deliverable | AcceptanceCriteria | Status | Notes
2026-02-15 | 2026-02-21 | Lobby construction, Tower Design Sprint 1, Enemy Design Sprint 1, Map Inspirations | Design Lead | TowerDesign_v0.1, EnemyTaxonomy_v0.1, MapIdeas_v0.1 | Each doc has at least one fully filled example | In Progress | Start lobby visuals; unblock modeling with tower/enemy/map specs
2026-02-22 | 2026-02-28 | Tower Models start, Tower Design Sprint 2, Tower Spec Finalization | Art Lead | TowerDesign_v1.0, TowerSpec | Specs signed off by artists/scripters | Planned | Modeling begins; finalize tower stats and abilities
2026-03-01 | 2026-03-07 | Enemy Models start, Enemy AI Spec | Dev Lead | EnemyDesign_v1.0, EnemyAISpec | Basic AI behavior trees defined | Planned | Ensure enemy behaviors are testable
2026-03-08 | 2026-03-14 | Map Prototypes, Level Scripting | Design Lead | MapPrototypes, Playtest Notes | 2–3 maps playable end-to-end | Planned | Test tower placement and pathing
2026-03-15 | 2026-03-21 | Integrate Towers/Enemies, Balance Pass 1, UI/UX | Dev Lead | BalanceReport_1, UI Mockups | No economy breaks in playtest | Planned | Ensure shop and HUD are functional
2026-03-22 | 2026-03-31 | Finishing Touches, QA, SOS System, DataStore Tests | QA | ReleaseCandidate_v0.1, Bug List | Stable demo, no critical bugs | Planned | Test persistence, matchmaking, economy
2026-04-01 | 2026-04-14 | Polish, Seasonal Quest Planning | Design Lead | QuestDesign_v1.0 | Quest tiers and rewards defined | Planned | Add polish and seasonal hooks
2026-04-15 | 2026-04-30 | Closed Alpha, Open Beta, Marketing Assets | Dev Lead | ClosedAlphaReport, BetaFeedback, PromoKit | Feedback collected, assets delivered | Planned | Prepare for public exposure

## Tower Design Tasks
ID | Name | Tier | GridFootprint | TixCost | EmeraldCost | BossReq | Role | BaseDamage | FireRate | Range | SpecialEffect | UpgradePath | VFXNotes | ServerHooks | PlaytestNotes
1 | Arrow Turret | Starter | 1x1 | 100 | 0 |  | Basic DPS | 10 | 1 | 5 | None | Lv2, Lv3 | Basic arrow shot | Auto-fire | Good early game
2 | Rapid Dart | Beginner | 1x1 | 150 | 0 |  | Fast DPS | 5 | 3 | 4 | None | Lv2, Lv3 | Fast dart VFX | Rapid fire | Test fire rate
3 | Glue Pad | Beginner | 1x1 | 120 | 0 |  | Slow | 0 | 0 | 3 | Slows enemies | Lv2, Lv3 | Sticky effect | Applies slow | Check stacking
4 | Bomb Lobber | Normal | 2x2 | 300 | 750 |  | AOE | 25 | 0.5 | 4 | Splash damage | Lv2, Lv3 | Explosion | AOE logic | Balance radius
5 | Flame Spitter | Normal | 1x1 | 350 | 750 |  | DOT | 3 | 5 | 3 | Burn over time | Lv2, Lv3 | Fire stream | Burn tick | Test burn stack
6 | Sniper Perch | Normal | 1x1 | 400 | 750 |  | Long-range | 50 | 0.2 | 12 | Piercing shot | Lv2, Lv3 | Scope flash | Line trace | Balance delay
7 | Tesla Coil | Marine | 2x2 | 600 | 1500 | Violent | Chain Lightning | 20 | 1 | 6 | Chains to 3 enemies | Lv2, Lv3 | Electric arcs | Chain logic | Test chaining
8 | Frost Tower | Marine | 2x2 | 550 | 1500 | Violent | AOE Slow | 0 | 0.5 | 5 | Freezes enemies | Lv2, Lv3 | Frost aura | Freeze effect | Check freeze duration
9 | Poison Injector | Marine | 1x1 | 500 | 1500 | Violent | DOT | 2 | 2 | 4 | Poison over time | Lv2, Lv3 | Green mist | Poison tick | Stacking test
10 | Shock Grid | Legendary | 2x2 | 800 | 1500 | Nightmare | Stun | 15 | 1.5 | 5 | Stuns enemies | Lv2, Lv3 | Electric pulse | Stun logic | Stun duration
11 | Mortar Battery | Legendary | 3x3 | 1000 | 1500 | Nightmare | Long-range AOE | 60 | 0.3 | 10 | High AOE | Lv2, Lv3 | Mortar shell | Arc projectile | Test splash
12 | Homing Launcher | Legendary | 2x2 | 900 | 1500 | Nightmare | Homing | 40 | 1 | 8 | Homing missiles | Lv2, Lv3 | Missile trail | Homing logic | Target switching

## Enemy Design Tasks
ID | Name | Category | HP | Speed | Armor | SpecialAbility | RewardTix | RewardEmeralds | SpawnWave | BehaviorNotes | CounterTowers
1 | Grunt | Basic | 100 | 1 | 0 | None | 10 | 0 | 1 | Standard enemy | Arrow Turret
2 | Runner | Fast | 50 | 2.5 | 0 | Speed burst | 8 | 0 | 2 | Fast but fragile | Rapid Dart
3 | Tank | Armored | 500 | 0.5 | 50 | None | 20 | 0 | 3 | Slow, high HP | Bomb Lobber
4 | Flyer | Flyer | 80 | 1.5 | 0 | Ignores ground | 12 | 0 | 4 | Bypasses ground towers | Sniper Perch
5 | Shielded | Shielded | 150 | 1 | 100 | Absorbs first hit | 15 | 0 | 5 | Shield blocks 1 hit | Tesla Coil
6 | Regenerator | Regenerator | 200 | 1 | 0 | Heals over time | 18 | 0 | 6 | Regenerates HP | Poison Injector
7 | Swarm | Swarm | 30 | 1.2 | 0 | Spawns in groups | 5 | 0 | 7 | Overwhelms with numbers | Flame Spitter
8 | Elite Brute | Elite | 600 | 0.8 | 75 | AOE slam | 30 | 500 | 8 | Mini-boss | Mortar Battery
9 | Caster | Caster | 150 | 1 | 0 | Ranged attack | 20 | 250 | 9 | Attacks towers | Sniper Perch
10 | Nightmare Overlord | Boss | 3000 | 0.6 | 200 | Summons minions | 100 | 2500 | 10 | Final boss | All Legendary

## Map Ideas
MapName | Theme | GridSize | BuildZones | PathNodes | MechanicalHook | Hazards | SuggestedDifficulty | VisualInspo | PlaytestGoals
Conveyor Coast | Industrial Port | 20x20 | Corners | Zigzag | Moving platforms | Water pits | Normal | Shipping containers, cranes | Test movement timing
Crystal Cavern | Underground | 18x18 | Center | Spiral | Low visibility | Falling rocks | DOOM | Glowing crystals | Test visibility limits
Skybridge | Floating Islands | 22x22 | Islands | Bridges | Elevation | Wind gusts | HEXEN | Clouds, floating rocks | Test vertical targeting
Lava Forge | Volcano | 20x20 | Edges | Loop | Lava flows | Lava damage | BLOOD | Molten metal, chains | Test hazard timing
Frostbite Fields | Tundra | 18x18 | Scattered | Straight | Slippery tiles | Ice cracks | Normal | Snow, aurora | Test slow effects
Cyber Core | Digital | 16x16 | Grid | Random | Teleport pads | Glitches | DOOM | Neon, circuits | Test teleport logic
Jungle Ruins | Overgrown | 20x20 | Center | Maze | Vines block view | Poison gas | HEXEN | Statues, moss | Test line of sight
Desert Mirage | Wasteland | 22x22 | Corners | Wave | Mirage clones | Sandstorms | BLOOD | Ruins, dunes | Test decoys
Haunted Hollow | Graveyard | 18x18 | Edges | Loop | Ghost phase | Fog | DOOM | Tombstones, fog | Test ghost mechanics
Skyline Siege | City Rooftops | 20x20 | Towers | Bridges | Zip lines | Falling debris | HEXEN | Neon signs | Test fast movement
Sunken Temple | Underwater | 16x16 | Center | Spiral | Water currents | Flooding | Normal | Coral, ruins | Test movement drag
Clockwork Keep | Steampunk | 20x20 | Corners | Rotating | Moving gears | Crushers | BLOOD | Cogs, steam | Test timing

## Playtest Schedule
Date | Type | Participants | Focus | Notes | Owner
2026-02-28 | Internal | Designers | Tower feel, pathing | Early prototype test | Design Lead
2026-03-03 | Internal | Designers + Devs | Enemy AI | Test wave logic | Dev Lead
2026-03-07 | Internal | Designers | Map flow | Test build zones | Design Lead
2026-03-10 | Internal | Designers + QA | Balance | XP/Tix pacing | QA
2026-03-14 | Internal | All | Full run | End-to-end test | QA
2026-03-17 | Internal | Designers | UI/UX | Shop and HUD | Design Lead
2026-03-21 | Internal | All | SOS system | Disconnect recovery | Dev Lead
2026-03-24 | Internal | QA | DataStore | Save/load test | QA
2026-03-28 | Internal | All | Final polish | Pre-alpha check | QA
2026-03-25 | Closed | 50 invited | Economy, feedback | Alpha test | QA
2026-04-20 | Open | Public | Retention, bugs | Beta launch | Dev Lead

## Economy & Balance Checkpoints
CheckpointDate | Metric | Target | Actual | Notes
2026-03-15 | Time-to-afford Normal tower | ≤1 day
2026-03-15 | Time-to-afford Marine tower | ≤2 weeks
2026-03-15 | Time-to-afford Legendary tower | ≥1 month
2026-03-15 | Emeralds/week | 5–20
2026-03-15 | XP per run | 200–2000

## Risk Register
RiskID | Risk | Impact | Likelihood | Mitigation | Owner | Status
1 | Specs before models | High | High | Require sign-off before modeling | Design Lead | Planned
2 | Economy inflation | High | Medium | Simulate economy weekly | Design Lead | Planned
3 | Instance disconnects | High | Medium | Implement SOS system | Dev Lead | Planned
4 | Legendary mandatory | Medium | Medium | Ensure Normal towers are viable | Design Lead | Planned
5 | AFK players | Medium | High | Contribution-based rewards | Dev Lead | Planned
6 | Data loss | High | Low | Test DataStore thoroughly | QA | Planned

## Templates
Template | Columns
Tower Template | ID, Name, Tier, GridFootprint, TixCost, EmeraldCost, BossReq, Role, BaseDamage, FireRate, Range, SpecialEffect, UpgradePath, VFXNotes, ServerHooks, PlaytestNotes
Enemy Template | ID, Name, Category, HP, Speed, Armor, SpecialAbility, RewardTix, RewardEmeralds, SpawnWave, BehaviorNotes, CounterTowers
Map Template | MapName, Theme, GridSize, BuildZones, PathNodes, MechanicalHook, Hazards, SuggestedDifficulty, VisualInspo, PlaytestGoals